## Slide 1
MENRE – BARMM
Directives, Accomplishment and Performance Assessment Tracking (DAPAT) 2022-2023
June 19, 2024

## Slide 2: 2022 Physical Accomplishment Report

## Slide 3: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. NATURAL RESOURCES ENFORCEMENT AND REGULATORY PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Increased areas of illegal logging hotspot neutralized | 30% (15) | 60% (9) | 60% |  |  |  | 
 | 2. Percentage of forest land protected against fire, poaching, pest and diseases, etc. | 100% (665,000) | 18.72% (124,519) | 18.72% |  |  |  | 
 | 3. Land records managed and digitized | 5% (74,670) | 316.80% (236,556) | 316.80% |  |  |  | 
 | 4. Efficiency of document tracking increased | 30% | 100% | 100% |  |  |  | 
 | 5. Percentage of illegally transported forest products apprehended | 10% (19,104 b.f) | 242.50% (46,327 b.f.) | 242.50% |  |  |  | 

## Slide 4: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. NATURAL RESOURCES ENFORCEMENT AND REGULATORY PROGRAM | Output indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of permits/ licenses/ clearances/ patents issued according to prescribe timelines | 90% (464) | 129% (598) | 129% |  |  |  | 
 | 2. No. of forest products monitoring check/choke points established | 5 | 2 | 40% |  |  |  | 
 | 3. No. of apprehended illegally transported forest products in BARMM | 19,104 | 46,327 | 242.5% |  |  |  | 
 | 4. Percentage of wildlife permits, certifications and/ or clearance applications acted upon within 7 working days from date of receipt | 100% (7) | 571% (40) | 571% |  |  |  | 

## Slide 5: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. NATURAL RESOURCES ENFORCEMENT AND REGULATORY PROGRAM | Output indicator(s): |  |  |  |  |  |  | 
 | 5. Percentage of land records inventoried, sorted, groomed, scanned and encoded | 5% (74,670) | 316.80% (236,556) | 316.80% |  |  |  | 
 | 6. Percentage of protected areas maintained and protected | 21% (4) | 100% (4) | 100% |  |  |  | 
 | 7. No. of Forest Land Use Plan facilitated, approved and legitimized | 5 | 3 | 60% |  |  |  | 
 | 8. Percentage of Forest Management Interactive Monitoring System Established | 80% | 20% | 20% |  |  |  | 

## Slide 6: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
2. NATURAL RESOURCES CONSERVATION AND DEVELOPMENT PROGRAM | Sub Program 1: Integrated Bangsamoro Greening Program (IBGP) |  |  |  |  |  |  | 
 | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of hectares reforested and rehabilitated | 52% (10,015) | 52% (5,182) | 52% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of hectares of open and denuded forestland rehabilitated | 5% (4,567.95) | 63% (2,888) | 63% |  |  |  | 
 | 2. Percentage of hectares planted area maintained and protected | 50% (5,950) | 39% (2,304) | 39% |  |  |  | 

## Slide 7: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
2. NATURAL RESOURCES CONSERVATION AND DEVELOPMENT PROGRAM | Sub program 2: Kayud Ka Bangsamoro (KKB) Convergence Program) |  |  |  |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of areas monitored | 9 | 12 | 133.3% |  |  |  | 
 | 2. No. of coordination meeting conducted | 6 | 17 | 283.3% |  |  |  | 

## Slide 8: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
3. MINERAL RESOURCES REGULATORY PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of revenues of BARMM mineral resources development | 75% (140,348,289.91) | 54.8% (80,493,405.00) | 54.8% |  |  |  | 
 | 2. Monitored mining permits/ contracts complying with laws, rules and regulations | 100% (8) | 100% (8) | 100% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. Mining permits/contracts monitored | 8 | 8 | 100% |  |  |  | 

## Slide 9: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
4. MINERAL RESOURCES AND GEOSCIENCES DEVELOPMENT PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of LGUs assisted in the identification of geology and mineral potential | 4% (5) | 80% (4) | 80% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. BARMM area surveyed for geology and mineral potential | 5 | 4 | 80% |  |  |  | 
 | 2. No. of Geologic Mapping Survey with laboratory analysis of rock samples conducted | 5 | 4 | 80% |  |  |  | 

## Slide 10: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
5. ENVIRONMENT ASSESSMENT AND PROTECTION PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Establishments that complied with the environmental conditions for the last two (2) years | 90% (73) | 49% (36) | 49% |  |  |  | 
 | 2. Increase in stakeholders environmental awareness and participation | 20% (24) | 117% (28) | 117% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. Projects monitored based on ECC conditions with reports submitted | 250 | 287 | 114.8% |  |  |  | 
 | 2. Information, Education and Communication (IEC) materials developed and disseminated | 500 | 510 | 102% |  |  |  | 
 | 3. Environmental research studies conducted for policy purposes | 4 | 4 | 100% |  |  |  | 
 | 4. Waterbodies classified/re-classified | 5 | 5 | 100% |  |  |  | 

## Slide 11: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
6. GEOLOGICAL RISK REDUCTION AND RESILIENCY PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. LGUs that included geohazard information in their Disaster Risk Reduction and Mitigation Plan Comprehensive Land Use Plan, and/ or Development Plan | 8% (10) | 60% (6) | 60% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. Cities and municipalities where vulnerabilities and risk assessments were conducted | 10 | 6 | 60% |  |  |  | 
 | 2. LGUs (cities/ municipalities) provided with information, education and communication campaigns on geohazards | 10 | 6 | 60% |  |  |  | 
 | 3. No. of Communication Education and Public Awareness (CEPA) on Landslide and Flood conducted | 10 | 6 | 60% |  |  |  | 
 | 4. No. of LGUs provided with computerized geohazard maps | 10 | 6 | 60% |  |  |  | 

## Slide 12: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
7. ENVIRONMENTAL REGULATIONS AND POLLUTION CONTROL PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of LGUs provided with technical assistance in the formulation of their Ecological Waste Management Plan | 25% (15) | 380% (57) | 380% |  |  |  | 
 | 2. Increase of industries complying with environmental standards | 35% (23) | 100% (23) | 100% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 2. Increase of industries complying with environmental standards | 90% (106) | 180% (191) | 180% |  |  |  | 
 | 1. Air and water pollution clearances processed and issued according to prescribed timeline of three (3) days | 5 | 6 | 120% |  |  |  | 

## Slide 13: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
8. ENERGY MANAGEMENT AND DEVELOPMENT PROGRAM | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of policies formulated that are effective and responsive | 20% | 20% | 100% |  |  |  | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of policies formulated and approved | 5 | 11 | 220% |  |  |  | 
 | 2. No. of surveys completed | 15 | 24 | 160% |  |  |  | 
 | 3. No. of coordination meetings conducted | 6 | 24 | 400% |  |  |  | 
 | 4. Remaining percentage of Bangsamoro Energy Development Plan Completed | 30% | 30% | 100% |  |  |  | 

## Slide 14: 2023 Physical Accomplishment Report

## Slide 15: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. LAND SURVEY, DISPOSITION, RECORDS AND KNOWLEDGE MANAGEMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 1. Land Administration and Management System (LAMS) | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage (%) of Land related data captured, stored, analyzed and information generated |  |  |  | 16.67% (231,085) | 11.21% (113,297) | 67.25% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of Land related data inventoried, sorted and groomed |  |  |  | 11,574 | 91,644 | 791.8% | 
 | 2. No. of land related data scanned |  |  |  | 118,523 | 59,111 | 49.98% | 
 | 3. No. of Land records encoded |  |  |  | 50,494 | 4,889 | 9.68% | 
 | 4. No. of land data generated |  |  |  | 50,494 | 0 | 0 | 

## Slide 16: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. LAND SURVEY, DISPOSITION, RECORDS AND KNOWLEDGE MANAGEMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 2. Inspection, Verification and Approval of all types of Survey (IVAS) | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Increased Percentage (%) of land area in hectares inspected, verified and approved |  |  |  | 15.85% (3,000) | 13.70% (2,592.7) | 86.4% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of Land surveys (in hectares) inspected, verified and approved |  |  |  | 3,000 | 2,592.7 | 86.42% | 

## Slide 17: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. LAND SURVEY, DISPOSITION, RECORDS AND KNOWLEDGE MANAGEMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 3. Land Records Management for BARMM, Cotabato City and 63 Special Geographic Areas | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage (%) of Land records managed and digitized |  |  |  | 16.67% (45,245) | 16.67% (45,245) | 100% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of system maintained and functional |  |  |  | 1 | 1 | 100% | 
 | 2. No. of Land -related applications received, tracked and issued/approved according to prescribed timelines |  |  |  | 477 | 396.0 | 83.01% | 
 | 3. No. of Land records (per sheet) for Cotabato City and 63 Barangays reproduced |  |  |  | 45,245 | 45,245 | 100% | 

## Slide 18: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs |  | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  |  | 2022 |  |  | 2023 |  |  | 
 |  |  | Targets | Accomp | % | Targets | Accomp | % | 
PROGRAM 2. ENVIRONMENTAL REGULATION COMPLIANCE,AMBIENT MONITORING and POLLUTION CONTROL PROGRAM |  |  |  |  |  |  |  |  | 
Sub Program 1: Environmental Regulation Compliance | Outcome Indicator(s): | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of industries permit and clearances compliance monitored | 1. Percentage of industries permit and clearances compliance monitored |  |  |  | 5% increase from 2020 permits released (261) | 351% (485) | 351% | 
 | 2. Percentage increase of revenue collection from BARMM environmental permits | 2. Percentage increase of revenue collection from BARMM environmental permits |  |  |  | 5% increase from 2021 revenue collection (626,799.92) | 352% (882,950) | 352% | 
 | Output Indicator(s): | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. of clearances (ECC and CNC) issued | 1. No. of clearances (ECC and CNC) issued |  |  |  | 120 | 242 | 201.7% | 
 | 2. No. of Permit to Operate (PTO) issued | 2. No. of Permit to Operate (PTO) issued |  |  |  | 48 | 126 | 262.5% | 
 | 3. No. of Wastewater Discharge Permit (WDP) issued | 3. No. of Wastewater Discharge Permit (WDP) issued |  |  |  | 20 | 54 | 270% | 
 | 4. No. of Pollution Control Officer Certificate of Accreditation approved | 4. No. of Pollution Control Officer Certificate of Accreditation approved |  |  |  | 65 | 38 | 58.5% | 
 | 5. No. of industries registered (Hazardous Waste Generators) | 5. No. of industries registered (Hazardous Waste Generators) |  |  |  | 6 | 15 | 250% | 
 | 6. No. of plans approved | 6. No. of Test plans approved |  |  |  | 10 | 0 | 0 | 
 | 7. No. of Permit to Transport (PTT) issued | 7. No. of Permit to Transport (PTT) issued |  |  |  | 21 | 10 | 47.6% | 
 | 8. No. of approved contract | 8. No. of approved contract |  |  |  | 1 | 0 | 0 | 

## Slide 19: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
PROGRAM 2. ENVIRONMENTAL REGULATION COMPLIANCE,AMBIENT MONITORING and POLLUTION CONTROL PROGRAM |  |  |  |  |  |  |  | 
Sub Program 2: Ambient Air and Water Baseline and Monitoring | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Ambient air and water quality in BARMM improved/maintained |  |  |  | (2) 1 water body classified, 1 Air Quality Monitoring established | 3 | 150% | 
 | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. of Monitoring Station established |  |  |  | 1 | 1 | 100% | 
 | 2. No. of water bodies classified |  |  |  | 1 | 2 | 100% | 

## Slide 20: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
PROGRAM 2. ENVIRONMENTAL REGULATION COMPLIANCE,AMBIENT MONITORING and POLLUTION CONTROL PROGRAM |  |  |  |  |  |  |  | 
Sub Program 3: Pollution Control and Compliance Monitoring | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage compliance of firms/establishment to all environmental laws |  |  |  | 100% (150) | 105% (156) | 105% | 
 | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. of firms monitored and complied with ECC conditions |  |  |  | 75 | 91 | 121.3% | 
 | 2. No. of firms monitored and complied with Clean Air Act |  |  |  | 150 | 156 | 104% | 
 | 3. No. of firms monitored and complied with Clean Water Act |  |  |  | 150 | 156 | 104% | 
 | 4. No. of firms monitored and complied with RA 6969 |  |  |  | 150 | 156 | 104% | 
 | 5. No. of observed Emission and Ambient Testing of accredited third party |  |  |  | 4 | 4 | 100% | 
 | 6. No. of Survey Firms with Polychlorinated Biphenyl (PCB) owners not registered |  |  |  | 1 | 1 | 100% | 
 | 7. No. of recommendation for Notice of Violation issued |  |  |  | 20 | 77 | 385% | 

## Slide 21: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
PROGRAM 2. ENVIRONMENTAL REGULATION COMPLIANCE,AMBIENT MONITORING and POLLUTION CONTROL PROGRAM |  |  |  |  |  |  |  | 
Sub Program 4: Solid Waste Management | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of LGUs provided with technical assistance on the Ecological Solid Waste Management Act |  |  |  | 19% (23) | 14% (17) | 74% | 
 | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. technical assistance provided to LGUs |  |  |  | 23 | 17 | 73.9% | 
 | 2. No. of sites assessed of proposed Sanitary Landfill Facilties (SLF) |  |  |  | 4 | 5 | 125% | 
 | 3. No. of Solid Waste Management (SWM) Plan monitored |  |  |  | 44 | 29 | 65.9% | 
 | 4. No. of open dumpsite closed and rehabilitated monitored |  |  |  | 10 | 12 | 120% | 
 | 5. No. of monitored and Assessed Material Recovery Facility (MRFs) and MRFs with composting facility |  |  |  | 40 | 40 | 100% | 
 | 6. No. of monitored Residual Containment Area (RCAs) |  |  |  | 20 | 25 | 125% | 
 | 7. No. of Sanitary Landfill Facilities (SLFs) monitored |  |  |  | 10 | 11 | 110% | 
 | 8. No. of ecofriendly schools |  |  |  | 5 | 0 | 0 | 
 | 9. No. of search for eco-friendly LGUs and BLGUs |  |  |  | 5 | 0 | 0 | 

## Slide 22: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
PROGRAM 2. ENVIRONMENTAL REGULATION COMPLIANCE,AMBIENT MONITORING and POLLUTION CONTROL PROGRAM |  |  |  |  |  |  |  | 
Sub Program 5: Climate Change | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Baseline data on GHG emission established |  |  |  | 1 GHG Inventory released (entry level) | 0 | 0 | 
 | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. trainings and meetings conducted |  |  |  | 1 | 1 | 100% | 
 | 2. No. of GHG Reports released |  |  |  | 1 | 0 | 0 | 
Sub Program 6: Annual Brown Environment Report | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Increased awareness on environemental protection and pollution control |  |  |  | 1 Annual Brown Environment Report released | 0 | 0 | 
 | Output Indicator(s): |  |  |  |  |  |  | 
 | 1. No. of copies for Brown Environment Report released |  |  |  | 1,000 | 0 | 0 | 

## Slide 23: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
3. NATURAL RESOURCES POLICY ENFORCEMENT, CONSERVATION AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 1: Policy Formulation and Development Program | Outcome Indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of response, effective and inclusive policy and guidelines related to forestry localized and enforced |  |  |  | 33% | 0 | 0 | 
 | Output Indicator |  |  |  |  |  |  | 
 | 1. No. of bill formulated related to forestry |  |  |  | 1 | 1 | 100% | 
 | 2. No. of forestry guidelines formulated |  |  |  | 2 | 4 | 200% | 

## Slide 24: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
3. NATURAL RESOURCES POLICY ENFORCEMENT, CONSERVATION AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 2: Forest Protection and Law Enforcement Program | Outcome Indicator |  |  |  |  |  |  | 
 | 1. Percentage increased of Municipalities illegal logging hotspot neutralized |  |  |  | 16% (10) | 80% (8) | 80% | 
 | 2. 688,051.72 hectares of forestland protected against fire, poaching, pest and diseases |  |  |  | 100% (688,051.72) | 71% (448,335.7) | 71% | 
 | 3. Percentage of apprehended illegally transported forest product in BARMM |  |  |  | 16.67% (2000) | 641.68% (12,833.5) | 641.68% | 
 | 4. Increased No. of permits/ license/clearance issued according to prescribed timelines |  |  |  | 100% (25) | 224% (61) | 224% | 
 | 5. Percentage of forest products monitoring check/choke points established |  |  |  | 20% (5) | 20% (2) | 40% | 
 | 6. Percentage of Forest Management Interactive Monitoring System established |  |  |  | 16% (279,296) | 16% | 100% | 
 | 7. Percentage of BARMM municipalities assisted in Forest Land Use Plan formulation |  |  |  | 10% (1) | 0 | 0 | 

## Slide 25: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
3. NATURAL RESOURCES POLICY ENFORCEMENT, CONSERVATION AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 2: Forest Protection and Law Enforcement Program | Output Indicator |  |  |  |  |  |  | 
 | 1. No. of Municipalities illegal logging hotspot neutralized |  |  |  | 10 | 8 | 80% | 
 | 2. No. forestland protected against fire, poaching, pest and deseases |  |  |  | 688,051.72 | 488,355.70 | 71% | 
 | 3. No. illegally transported forest product apprehended |  |  |  | 2000 | 12,833.50 | 641.6% | 
 | 4. No. of permits/ license/clearance issued according to prescribed timelines |  |  |  | 25 | 61 | 244% | 
 | 5. No. of establiished check/choke points |  |  |  | 5 | 2 | 40% | 
 | 6. Established Interactive Monitoring System |  |  |  | 16% | 16% | 100% | 
 | 7. No. of legitimized and approved FLUP |  |  |  | 1 | 0 | 0 | 

## Slide 26: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp |  | % | 
3. NATURAL RESOURCES POLICY ENFORCEMENT, CONSERVATION AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  |  | 
Sub-Program 3. Conservation and Management Program | 3.1. IBGP-Integrated Bangsamoro Greening Program |  |  |  |  |  |  |  | 
 | Outcome Indicator |  |  |  |  |  |  |  | 
 | 1. Percentage of Hectares reforested and Rehabilitated |  |  |  | 2% of Baseline (159,159 Baseline) (3,183.18) | 81.7% (2,431.44) | 76% (2,431.44) | 76% | 
 | Output Indicator |  |  |  |  |  |  |  | 
 | 1. No. of Hectares of open and denuded forestland rehabilitate |  |  |  | 2,410 | 1,818.46 | 1,818.46 | 75.5% | 
 | 2. No. of hectares of forestland rehabilitated |  |  |  | 760 | 606.98 | 606.98 | 80% | 
 | 3. No. of hectares of planted area maintained and protected |  |  |  | 1,080 | 1,038.25 | 1,038.25 | 96% | 
 | 3.2. Kayud Ka Bangsamoro Convergence |  |  |  |  |  |  |  | 
 | Output Indicator |  |  |  |  |  |  |  | 
 | 1. No. of Area Monitored |  |  |  | 15 | 16 | 16 | 106.7% | 
 | 2. No. of workshop/ seminar/ meeting attended |  |  |  | 25 | 16 | 16 | 64% | 

## Slide 27: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
3. NATURAL RESOURCES POLICY ENFORCEMENT, CONSERVATION AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 4. Social Forestry Activity | Output Indicator |  |  |  |  |  |  | 
 | 1. No. of IEC Materials developed |  |  |  | 3 | 2 | 67% | 
 | 2. No. of documentation packaged |  |  |  | 1 | 1 | 100% | 

## Slide 28: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
4. MINERAL RESOURCES AND GEOSCIENCES DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 1: Mineral Resources Regulatory Program | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of revenues of BARMM from mineral resources development |  |  |  | 50% | 46.18% (Php 70,522,151.75) | 92% | 
 | 2. Monitoring of mining companies complying with laws, rules and regulations conducted |  |  |  | 20 | 20 | 100% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of mining permits/contracts monitored |  |  |  | 20 | 20 | 100% | 
 | 2. No of mining rights/contracts/permits issued/endorsed |  |  |  | 120 | 121 | 100.83% | 

## Slide 29: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
4. MINERAL RESOURCES AND GEOSCIENCES DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 2: Geologic Mapping Program | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of LGUs assisted in the identification of geology and mineral potential |  |  |  | 3% (4) | 3% (4) | 100% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of BARMM area surveyed for geology and mineral potential |  |  |  | 4 | 4 | 100% | 

## Slide 30: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
4. MINERAL RESOURCES AND GEOSCIENCES DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 3: Geological Risk Reduction and Resiliency Program | Outcome indicator(s): |  |  |  |  |  |  | 
 | 1. Percentage of LGUs provided with geohazard susceptibility data and vulnerability and risk assessment data |  |  |  | 3% (3) | 3% (3) | 100% | 
 | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No. of LGUs where geohazard assessment and mapping were conducted |  |  |  | 3 | 3 | 100% | 
 | 2. No. of technical reports and maps of the geohazard and risk assessments furnished to relevant BARMM Ministries |  |  |  | 3 | 3 | 100% | 
 | 3. No. of LGUs where Communication, Education, and Public Awareness Campaigns on geohazards were conducted |  |  |  | 3 | 3 | 100% | 
 | 4. No. of Geohazard Certificates, Geological Site Scoping/Investigation Reports in relation to their proposed projects/site development provided to the stakeholders |  |  |  | 20 | 20 | 100% | 

## Slide 31: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
4. MINERAL RESOURCES AND GEOSCIENCES DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub-Program 4. Mineral Reservation Program | Output indicator(s): |  |  |  |  |  |  | 
 | 1. No, of new mineral reservation area assessed/endorsed for declaration |  |  |  | 1 | 1 | 100 | 

## Slide 32: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
5. BIODIVERSITY MANAGEMENT, RESEARCH AND PROTECTED AREA DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 1: Biodiversity Management and Regulatorion Program | Outcome Indicator(s) |  |  |  |  |  |  | 
 | 1. Percentage of Wildlife permit, certification and/or clearance acted |  |  |  | 100% | 700% | 700% | 
 | 2. Percentage of Wildlife rescued and rehabilitated |  |  |  | 100% | 116.7% | 116.7% | 
 | 3. Percentage of BARMM Areas with Wildlife Center Establishment |  |  |  | 100% | 0 | 0 | 
 | Output Indicator(s) |  |  |  |  |  |  | 
 | 1. No.of wildlife permit issued |  |  |  | 7 | 49 | 700% | 
 | 2. No.of wildlife rescued and rehabilitated |  |  |  | 6 | 7 | 116.7% | 
 | 3. No.of wildlife inventoried |  |  |  | 1 | 1 | 100% | 
 | 4. No. of Wildlife Rescue Center Established |  |  |  | 1 | 0 | 0 | 

## Slide 33: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
5. BIODIVERSITY MANAGEMENT, RESEARCH AND PROTECTED AREA DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 2: Protected Area Development Management Program | Outcome Indicator(s) |  |  |  |  |  |  | 
 | 1. Percentage of eco - tourism assessed |  |  |  | 100% (1) | 100% (1) | 100% | 
 | 2. Percentage of protected area managed and maintained |  |  |  | 100% (1) | 200% (2) | 200% | 
 | 3. Percentage of inland wetland conserved and monitored |  |  |  | 100% (1) | 100% (1) | 100% | 
 | Output Indicator(s) |  |  |  |  |  |  | 
 | 1. No. of eco - tourism site assessed |  |  |  | 1 | 1 | 100% | 
 | 2. No. of protected area managed, maintained and protected |  |  |  | 1 | 2 | 200% | 
 | 3. No. of inland wetland conserved and monitored |  |  |  | 1 | 1 | 100% | 

## Slide 34: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
5. BIODIVERSITY MANAGEMENT, RESEARCH AND PROTECTED AREA DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 3: Research and Development Program | Outcome Indicator(s) |  |  |  |  |  |  | 
 | 1. Percentage of environmental research studies conducted for policy purposes |  |  |  | 100% | 76% | 76% | 
 | Output Indicator(s) |  |  |  |  |  |  | 
 | 1. No.of research studies conducted |  |  |  | 4 | 4 | 100% | 
 | 2. No.of data collected/gathered |  |  |  | 8 | 5 | 62.5% | 
 | 3. No.of collected data analyzed |  |  |  | 8 | 5 | 62.5% | 

## Slide 35: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
6. ENERGY MANAGEMENT AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 1: ENERGY MANAGEMENT AND DEVELOPMENT PROGRAM | Outcoume Indicator: |  |  |  |  |  |  | 
 | 1. Percentage of policies formulated, adopted, implemented, and monitored |  |  |  | 50% | 50% | 100% | 
 | Output Indicator: |  |  |  |  |  |  | 
 | 1. No. of Effective and Efficient Policies Formulated |  |  |  | 8 | 9 | 112.5% | 
 | 2. No. of Potential Energy Resources Surveyed and Validated |  |  |  | 15 | 21 | 140% | 
 | 3. No. of energy sector institutions capacitated |  |  |  | 5 | 21 | 420% | 
 | 4. No. of technical assistance/ evaluation of energy stakeholders conducted |  |  |  | 2 | 4 | 200% | 

## Slide 36: Physical Accomplishment Report BARMM - GAAB (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
6. ENERGY MANAGEMENT AND DEVELOPMENT PROGRAM |  |  |  |  |  |  |  | 
Sub Program 2: ENERGY REGULATORY AND ENHANCEMENT PROGRAM | Outcoume Indicator: |  |  |  |  |  |  | 
 | 1. Percentage increase of revenue in the energy sector |  |  |  | 100% (80,000) | 221% (176,760) | 221% | 
 | 2. Percentage increase of industry players regulated, supervised |  |  |  | 100% (14) | 243% (34) | 243% | 
 | 3. Percentage increase of services in the energy sector rendered |  |  |  | 50% (6) | 134% (8) | 134% | 
 | Output Indicator: |  |  |  |  |  |  | 
 | 1. No. of certification / permits / accreditations / acknowledgements / endorsements issued |  |  |  | 10 | 37 | 370% | 
 | 2. No. of monitoring activities / inspections conducted |  |  |  | 20 | 41 | 205% | 
 | 3. No. of information, education, communication, and other promotional activities conducted |  |  |  | 20 | 40 | 200% | 
 | 4. No. of coordination meetings conducted |  |  |  | 15 | 16 | 106.7% | 

## Slide 37: B. Physical Accomplishment Report Nationally Funded PPAs (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. |  |  |  |  |  |  |  | 
2. |  |  |  |  |  |  |  | 
3 |  |  |  |  |  |  |  | 
4. |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  | 
Note: The physical report should include both the actual figures and the equivalent percentage for better appreciation of the data. For agency with activity target or other physical target, indicate the unit of measurement of physical targets
N/A

## Slide 38: TDIF

## Slide 39: D. Physical Accomplishment Report TDIF Funded PPAs (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment as of May 31, 2024 |  |  | Remarks
 |  | Targets | Accomp | % | 
TDIF 2022 |  |  |  |  | 
1. Solar Streetlights for Island Province Barangays | Number of Solar Streetlights for Mainland Island Province Barangays installed | 4 sets | 4 sets | 100% | Completed
2. Solar Streetlights for Mainland Province Barangays | Number of Solar Streetlights for Mainland Province Barangays installed | 4 sets | 4 sets | 100% | completed
3. Procurement of 37.5 kVa distribution transformer with installation accessories | Number of 37.5 kVa distribution transformer with installation accessories distributed to selected Electric Cooperatives | 1 set | 0 | 0 | On going procurement
4. Procurement of safety devices for distribution lines of electric cooperatives | Number of safety devices distributed to selected Electric Cooperatives | 1 set | 0 | 0 | On going procurement
5. Vehicle 4x4 for Landfield Investigation Activities | Number of 4x4 vehicles procured | 4 | 4 | 100% | Completed

## Slide 40: D. Physical Accomplishment Report TDIF Funded PPAs (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment as of May 2024 |  |  | Remarks
 |  | Targets | Accomp | % | 
TDIF 2023 |  |  |  |  | 
INSTALLATION OF MODERN METERING SYSTEM FOR RESIDENTIAL CUSTOMERS OF ELECTRIC COOPERATIVES (ECS) IN BARMM REGION | Number of Modern Metering System distributed to selected beneficiaries | 1 lot | 0 | 0 | 
2. PROVISION OF GARBAGE TRUCK COMPACTOR | Number of Garbage Truck Compactor provided to selected beneficiary | 1 Unit | 0 | 0 | On-going procurement
3. PLASTIC SHREDDER | Number of Plastic Shredder provided to selected beneficiary | 1 Unit | 0 | 0 | On-going procurement
4. UPGRATING OF DISTRIBUTION TRANSFORMERS FOR RESIDENTIAL CUSTOMERS OF ELECTRIC COOPERATIVES (ECS) IN BARMM REGION | Number distribution transformers distributed to selected beneficiaries | 1 lot | 0 | 0 | 

## Slide 41: C. Physical Accomplishment Report ODA Funded PPAs (FY 2022-2023)
PPAs | Performance Indicator | Physical Targets and Accomplishment |  |  |  |  |  | Remarks
 |  | 2022 |  |  | 2023 |  |  | 
 |  | Targets | Accomp | % | Targets | Accomp | % | 
1. |  |  |  |  |  |  |  | 
2. |  |  |  |  |  |  |  | 
3 |  |  |  |  |  |  |  | 
4. |  |  |  |  |  |  |  | 
5 |  |  |  |  |  |  |  | 
Note:
*The physical report should include both the actual figures and the equivalent percentage for better appreciation of the data. For agency with activity target or other physical target, indicate the unit of measurement of physical targets
**The MOAs may modify the form on a yearly basis if they have different programs by year
N/A

## Slide 42: Issues/Concerns and Recommendations
Issues/Concerns | Recommendations | Priorities for 2024 and 2025